{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"defined_names":2},"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":73,"n_cols":20,"rows_kept":73,"merged":[[0,0,0,12],[1,0,1,12],[2,0,2,12],[3,5,3,6],[3,7,3,8],[3,9,3,11],[13,0,13,1],[14,0,14,12],[15,0,15,4],[15,6,15,7],[15,8,15,12],[17,0,17,12],[18,0,18,12],[19,0,19,12],[19,13,19,25],[19,26,19,38],[19,39,19,51],[19,52,19,64],[19,65,19,77],[19,78,19,90],[19,91,19,103],[19,104,19,116],[19,117,19,129],[19,130,19,142],[19,143,19,155],[19,156,19,168],[19,169,19,181],[19,182,19,194],[19,195,19,207],[19,208,19,220],[19,221,19,233],[19,234,19,246],[19,247,19,259],[19,260,19,272],[19,273,19,285],[19,286,19,298],[19,299,19,311],[19,312,19,324],[19,325,19,337],[19,338,19,350],[19,351,19,363],[19,364,19,376],[19,377,19,389],[19,390,19,402],[19,403,19,415],[19,416,19,428],[19,429,19,441],[19,442,19,454],[19,455,19,467],[19,468,19,480],[19,481,19,493],[19,494,19,506],[19,507,19,519],[19,520,19,532],[19,533,19,545],[19,546,19,558],[19,559,19,571],[19,572,19,584],[19,585,19,597],[19,598,19,610],[19,611,19,623],[19,624,19,636],[19,637,19,649],[19,650,19,662],[19,663,19,675],[19,676,19,688],[19,689,19,701],[19,702,19,714],[19,715,19,727],[19,728,19,740],[19,741,19,753],[19,754,19,766],[19,767,19,779],[19,780,19,792],[19,793,19,805],[19,806,19,818],[19,819,19,831],[19,832,19,844],[19,845,19,857],[19,858,19,870],[19,871,19,883],[19,884,19,896],[19,897,19,909],[19,910,19,922],[19,923,19,935],[19,936,19,948],[19,949,19,961],[19,962,19,974],[19,975,19,987],[19,988,19,1000],[19,1001,19,1013],[19,1014,19,1026],[19,1027,19,1039],[19,1040,19,1052],[19,1053,19,1065],[19,1066,19,1078],[19,1079,19,1091],[19,1092,19,1104],[19,1105,19,1117],[19,1118,19,1130],[19,1131,19,1143],[19,1144,19,1156],[19,1157,19,1169],[19,1170,19,1182],[19,1183,19,1195],[19,1196,19,1208],[19,1209,19,1221],[19,1222,19,1234],[19,1235,19,1247],[19,1248,19,1260],[19,1261,19,1273],[19,1274,19,1286],[19,1287,19,1299],[19,1300,19,1312],[19,1313,19,1325],[19,1326,19,1338],[19,1339,19,1351],[19,1352,19,1364],[19,1365,19,1377],[19,1378,19,1390],[19,1391,19,1403],[19,1404,19,1416],[19,1417,19,1429],[19,1430,19,1442],[19,1443,19,1455],[19,1456,19,1468],[19,1469,19,1481],[19,1482,19,1494],[19,1495,19,1507],[19,1508,19,1520],[19,1521,19,1533],[19,1534,19,1546],[19,1547,19,1559],[19,1560,19,1572],[19,1573,19,1585],[19,1586,19,1598],[19,1599,19,1611],[19,1612,19,1624],[19,1625,19,1637],[19,1638,19,1650],[19,1651,19,1663],[19,1664,19,1676],[19,1677,19,1689],[19,1690,19,1702],[19,1703,19,1715],[19,1716,19,1728],[19,1729,19,1741],[19,1742,19,1754],[19,1755,19,1767],[19,1768,19,1780],[19,1781,19,1793],[19,1794,19,1806],[19,1807,19,1819],[19,1820,19,1832],[19,1833,19,1845],[19,1846,19,1858],[19,1859,19,1871],[19,1872,19,1884],[19,1885,19,1897],[19,1898,19,1910],[19,1911,19,1923],[19,1924,19,1936],[19,1937,19,1949],[19,1950,19,1962],[19,1963,19,1975],[19,1976,19,1988],[19,1989,19,2001],[19,2002,19,2014],[19,2015,19,2027],[19,2028,19,2040],[19,2041,19,2053],[19,2054,19,2066],[19,2067,19,2079],[19,2080,19,2092],[19,2093,19,2105],[19,2106,19,2118],[19,2119,19,2131],[19,2132,19,2144],[19,2145,19,2157],[19,2158,19,2170],[19,2171,19,2183],[19,2184,19,2196],[19,2197,19,2209],[19,2210,19,2222],[19,2223,19,2235],[19,2236,19,2248],[19,2249,19,2261],[19,2262,19,2274],[19,2275,19,2287],[19,2288,19,2300],[19,2301,19,2313],[19,2314,19,2326],[19,2327,19,2339],[19,2340,19,2352],[19,2353,19,2365],[19,2366,19,2378],[19,2379,19,2391],[19,2392,19,2404],[19,2405,19,2417],[19,2418,19,2430],[19,2431,19,2443],[19,2444,19,2456],[19,2457,19,2469],[19,2470,19,2482],[19,2483,19,2495],[19,2496,19,2508],[19,2509,19,2521],[19,2522,19,2534],[19,2535,19,2547],[19,2548,19,2560],[19,2561,19,2573],[19,2574,19,2586],[19,2587,19,2599],[19,2600,19,2612],[19,2613,19,2625],[19,2626,19,2638],[19,2639,19,2651],[19,2652,19,2664],[19,2665,19,2677],[19,2678,19,2690],[19,2691,19,2703],[19,2704,19,2716],[19,2717,19,2729],[19,2730,19,2742],[19,2743,19,2755],[19,2756,19,2768],[19,2769,19,2781],[19,2782,19,2794],[19,2795,19,2807],[19,2808,19,2820],[19,2821,19,2833],[19,2834,19,2846],[19,2847,19,2859],[19,2860,19,2872],[19,2873,19,2885],[19,2886,19,2898],[19,2899,19,2911],[19,2912,19,2924],[19,2925,19,2937],[19,2938,19,2950],[19,2951,19,2963],[19,2964,19,2976],[19,2977,19,2989],[19,2990,19,3002],[19,3003,19,3015],[19,3016,19,3028],[19,3029,19,3041],[19,3042,19,3054],[19,3055,19,3067],[19,3068,19,3080],[19,3081,19,3093],[19,3094,19,3106],[19,3107,19,3119],[19,3120,19,3132],[19,3133,19,3145],[19,3146,19,3158],[19,3159,19,3171],[19,3172,19,3184],[19,3185,19,3197],[19,3198,19,3210],[19,3211,19,3223],[19,3224,19,3236],[19,3237,19,3249],[19,3250,19,3262],[19,3263,19,3275],[19,3276,19,3288],[19,3289,19,3301],[19,3302,19,3314],[19,3315,19,3327],[19,3328,19,3340],[19,3341,19,3353],[19,3354,19,3366],[19,3367,19,3379],[19,3380,19,3392],[19,3393,19,3405],[19,3406,19,3418],[19,3419,19,3431],[19,3432,19,3444],[19,3445,19,3457],[19,3458,19,3470],[19,3471,19,3483],[19,3484,19,3496],[19,3497,19,3509],[19,3510,19,3522],[19,3523,19,3535],[19,3536,19,3548],[19,3549,19,3561],[19,3562,19,3574],[19,3575,19,3587],[19,3588,19,3600],[19,3601,19,3613],[19,3614,19,3626],[19,3627,19,3639],[19,3640,19,3652],[19,3653,19,3665],[19,3666,19,3678],[19,3679,19,3691],[19,3692,19,3704],[19,3705,19,3717],[19,3718,19,3730],[19,3731,19,3743],[19,3744,19,3756],[19,3757,19,3769],[19,3770,19,3782],[19,3783,19,3795],[19,3796,19,3808],[19,3809,19,3821],[19,3822,19,3834],[19,3835,19,3847],[19,3848,19,3860],[19,3861,19,3873],[19,3874,19,3886],[19,3887,19,3899],[19,3900,19,3912],[19,3913,19,3925],[19,3926,19,3938],[19,3939,19,3951],[19,3952,19,3964],[19,3965,19,3977],[19,3978,19,3990],[19,3991,19,4003],[19,4004,19,4016],[19,4017,19,4029],[19,4030,19,4042],[19,4043,19,4055],[19,4056,19,4068],[19,4069,19,4081],[19,4082,19,4094],[19,4095,19,4107],[19,4108,19,4120],[19,4121,19,4133],[19,4134,19,4146],[19,4147,19,4159],[19,4160,19,4172],[19,4173,19,4185],[19,4186,19,4198],[19,4199,19,4211],[19,4212,19,4224],[19,4225,19,4237],[19,4238,19,4250],[19,4251,19,4263],[19,4264,19,4276],[19,4277,19,4289],[19,4290,19,4302],[19,4303,19,4315],[19,4316,19,4328],[19,4329,19,4341],[19,4342,19,4354],[19,4355,19,4367],[19,4368,19,4380],[19,4381,19,4393],[19,4394,19,4406],[19,4407,19,4419],[19,4420,19,4432],[19,4433,19,4445],[19,4446,19,4458],[19,4459,19,4471],[19,4472,19,4484],[19,4485,19,4497],[19,4498,19,4510],[19,4511,19,4523],[19,4524,19,4536],[19,4537,19,4549],[19,4550,19,4562],[19,4563,19,4575],[19,4576,19,4588],[19,4589,19,4601],[19,4602,19,4614],[19,4615,19,4627],[19,4628,19,4640],[19,4641,19,4653],[19,4654,19,4666],[19,4667,19,4679],[19,4680,19,4692],[19,4693,19,4705],[19,4706,19,4718],[19,4719,19,4731],[19,4732,19,4744],[19,4745,19,4757],[19,4758,19,4770],[19,4771,19,4783],[19,4784,19,4796],[19,4797,19,4809],[19,4810,19,4822],[19,4823,19,4835],[19,4836,19,4848],[19,4849,19,4861],[19,4862,19,4874],[19,4875,19,4887],[19,4888,19,4900],[19,4901,19,4913],[19,4914,19,4926],[19,4927,19,4939],[19,4940,19,4952],[19,4953,19,4965],[19,4966,19,4978],[19,4979,19,4991],[19,4992,19,5004],[19,5005,19,5017],[19,5018,19,5030],[19,5031,19,5043],[19,5044,19,5056],[19,5057,19,5069],[19,5070,19,5082],[19,5083,19,5095],[19,5096,19,5108],[19,5109,19,5121],[19,5122,19,5134],[19,5135,19,5147],[19,5148,19,5160],[19,5161,19,5173],[19,5174,19,5186],[19,5187,19,5199],[19,5200,19,5212],[19,5213,19,5225],[19,5226,19,5238],[19,5239,19,5251],[19,5252,19,5264],[19,5265,19,5277],[19,5278,19,5290],[19,5291,19,5303],[19,5304,19,5316],[19,5317,19,5329],[19,5330,19,5342],[19,5343,19,5355],[19,5356,19,5368],[19,5369,19,5381],[19,5382,19,5394],[19,5395,19,5407],[19,5408,19,5420],[19,5421,19,5433],[19,5434,19,5446],[19,5447,19,5459],[19,5460,19,5472],[19,5473,19,5485],[19,5486,19,5498],[19,5499,19,5511],[19,5512,19,5524],[19,5525,19,5537],[19,5538,19,5550],[19,5551,19,5563],[19,5564,19,5576],[19,5577,19,5589],[19,5590,19,5602],[19,5603,19,5615],[19,5616,19,5628],[19,5629,19,5641],[19,5642,19,5654],[19,5655,19,5667],[19,5668,19,5680],[19,5681,19,5693],[19,5694,19,5706],[19,5707,19,5719],[19,5720,19,5732],[19,5733,19,5745],[19,5746,19,5758],[19,5759,19,5771],[19,5772,19,5784],[19,5785,19,5797],[19,5798,19,5810],[19,5811,19,5823],[19,5824,19,5836],[19,5837,19,5849],[19,5850,19,5862],[19,5863,19,5875],[19,5876,19,5888],[19,5889,19,5901],[19,5902,19,5914],[19,5915,19,5927],[19,5928,19,5940],[19,5941,19,5953],[19,5954,19,5966],[19,5967,19,5979],[19,5980,19,5992],[19,5993,19,6005],[19,6006,19,6018],[19,6019,19,6031],[19,6032,19,6044],[19,6045,19,6057],[19,6058,19,6070],[19,6071,19,6083],[19,6084,19,6096],[19,6097,19,6109],[19,6110,19,6122],[19,6123,19,6135],[19,6136,19,6148],[19,6149,19,6161],[19,6162,19,6174],[19,6175,19,6187],[19,6188,19,6200],[19,6201,19,6213],[19,6214,19,6226],[19,6227,19,6239],[19,6240,19,6252],[19,6253,19,6265],[19,6266,19,6278],[19,6279,19,6291],[19,6292,19,6304],[19,6305,19,6317],[19,6318,19,6330],[19,6331,19,6343],[19,6344,19,6356],[19,6357,19,6369],[19,6370,19,6382],[19,6383,19,6395],[19,6396,19,6408],[19,6409,19,6421],[19,6422,19,6434],[19,6435,19,6447],[19,6448,19,6460],[19,6461,19,6473],[19,6474,19,6486],[19,6487,19,6499],[19,6500,19,6512],[19,6513,19,6525],[19,6526,19,6538],[19,6539,19,6551],[19,6552,19,6564],[19,6565,19,6577],[19,6578,19,6590],[19,6591,19,6603],[19,6604,19,6616],[19,6617,19,6629],[19,6630,19,6642],[19,6643,19,6655],[19,6656,19,6668],[19,6669,19,6681],[19,6682,19,6694],[19,6695,19,6707],[19,6708,19,6720],[19,6721,19,6733],[19,6734,19,6746],[19,6747,19,6759],[19,6760,19,6772],[19,6773,19,6785],[19,6786,19,6798],[19,6799,19,6811],[19,6812,19,6824],[19,6825,19,6837],[19,6838,19,6850],[19,6851,19,6863],[19,6864,19,6876],[19,6877,19,6889],[19,6890,19,6902],[19,6903,19,6915],[19,6916,19,6928],[19,6929,19,6941],[19,6942,19,6954],[19,6955,19,6967],[19,6968,19,6980],[19,6981,19,6993],[19,6994,19,7006],[19,7007,19,7019],[19,7020,19,7032],[19,7033,19,7045],[19,7046,19,7058],[19,7059,19,7071],[19,7072,19,7084],[19,7085,19,7097],[19,7098,19,7110],[19,7111,19,7123],[19,7124,19,7136],[19,7137,19,7149],[19,7150,19,7162],[19,7163,19,7175],[19,7176,19,7188],[19,7189,19,7201],[19,7202,19,7214],[19,7215,19,7227],[19,7228,19,7240],[19,7241,19,7253],[19,7254,19,7266],[19,7267,19,7279],[19,7280,19,7292],[19,7293,19,7305],[19,7306,19,7318],[19,7319,19,7331],[19,7332,19,7344],[19,7345,19,7357],[19,7358,19,7370],[19,7371,19,7383],[19,7384,19,7396],[19,7397,19,7409],[19,7410,19,7422],[19,7423,19,7435],[19,7436,19,7448],[19,7449,19,7461],[19,7462,19,7474],[19,7475,19,7487],[19,7488,19,7500],[19,7501,19,7513],[19,7514,19,7526],[19,7527,19,7539],[19,7540,19,7552],[19,7553,19,7565],[19,7566,19,7578],[19,7579,19,7591],[19,7592,19,7604],[19,7605,19,7617],[19,7618,19,7630],[19,7631,19,7643],[19,7644,19,7656],[19,7657,19,7669],[19,7670,19,7682],[19,7683,19,7695],[19,7696,19,7708],[19,7709,19,7721],[19,7722,19,7734],[19,7735,19,7747],[19,7748,19,7760],[19,7761,19,7773],[19,7774,19,7786],[19,7787,19,7799],[19,7800,19,7812],[19,7813,19,7825],[19,7826,19,7838],[19,7839,19,7851],[19,7852,19,7864],[19,7865,19,7877],[19,7878,19,7890],[19,7891,19,7903],[19,7904,19,7916],[19,7917,19,7929],[19,7930,19,7942],[19,7943,19,7955],[19,7956,19,7968],[19,7969,19,7981],[19,7982,19,7994],[19,7995,19,8007],[19,8008,19,8020],[19,8021,19,8033],[19,8034,19,8046],[19,8047,19,8059],[19,8060,19,8072],[19,8073,19,8085],[19,8086,19,8098],[19,8099,19,8111],[19,8112,19,8124],[19,8125,19,8137],[19,8138,19,8150],[19,8151,19,8163],[19,8164,19,8176],[19,8177,19,8189],[19,8190,19,8202],[19,8203,19,8215],[19,8216,19,8228],[19,8229,19,8241],[19,8242,19,8254],[19,8255,19,8267],[19,8268,19,8280],[19,8281,19,8293],[19,8294,19,8306],[19,8307,19,8319],[19,8320,19,8332],[19,8333,19,8345],[19,8346,19,8358],[19,8359,19,8371],[19,8372,19,8384],[19,8385,19,8397],[19,8398,19,8410],[19,8411,19,8423],[19,8424,19,8436],[19,8437,19,8449],[19,8450,19,8462],[19,8463,19,8475],[19,8476,19,8488],[19,8489,19,8501],[19,8502,19,8514],[19,8515,19,8527],[19,8528,19,8540],[19,8541,19,8553],[19,8554,19,8566],[19,8567,19,8579],[19,8580,19,8592],[19,8593,19,8605],[19,8606,19,8618],[19,8619,19,8631],[19,8632,19,8644],[19,8645,19,8657],[19,8658,19,8670],[19,8671,19,8683],[19,8684,19,8696],[19,8697,19,8709],[19,8710,19,8722],[19,8723,19,8735],[19,8736,19,8748],[19,8749,19,8761],[19,8762,19,8774],[19,8775,19,8787],[19,8788,19,8800],[19,8801,19,8813],[19,8814,19,8826],[19,8827,19,8839],[19,8840,19,8852],[19,8853,19,8865],[19,8866,19,8878],[19,8879,19,8891],[19,8892,19,8904],[19,8905,19,8917],[19,8918,19,8930],[19,8931,19,8943],[19,8944,19,8956],[19,8957,19,8969],[19,8970,19,8982],[19,8983,19,8995],[19,8996,19,9008],[19,9009,19,9021],[19,9022,19,9034],[19,9035,19,9047],[19,9048,19,9060],[19,9061,19,9073],[19,9074,19,9086],[19,9087,19,9099],[19,9100,19,9112],[19,9113,19,9125],[19,9126,19,9138],[19,9139,19,9151],[19,9152,19,9164],[19,9165,19,9177],[19,9178,19,9190],[19,9191,19,9203],[19,9204,19,9216],[19,9217,19,9229],[19,9230,19,9242],[19,9243,19,9255],[19,9256,19,9268],[19,9269,19,9281],[19,9282,19,9294],[19,9295,19,9307],[19,9308,19,9320],[19,9321,19,9333],[19,9334,19,9346],[19,9347,19,9359],[19,9360,19,9372],[19,9373,19,9385],[19,9386,19,9398],[19,9399,19,9411],[19,9412,19,9424],[19,9425,19,9437],[19,9438,19,9450],[19,9451,19,9463],[19,9464,19,9476],[19,9477,19,9489],[19,9490,19,9502],[19,9503,19,9515],[19,9516,19,9528],[19,9529,19,9541],[19,9542,19,9554],[19,9555,19,9567],[19,9568,19,9580],[19,9581,19,9593],[19,9594,19,9606],[19,9607,19,9619],[19,9620,19,9632],[19,9633,19,9645],[19,9646,19,9658],[19,9659,19,9671],[19,9672,19,9684],[19,9685,19,9697],[19,9698,19,9710],[19,9711,19,9723],[19,9724,19,9736],[19,9737,19,9749],[19,9750,19,9762],[19,9763,19,9775],[19,9776,19,9788],[19,9789,19,9801],[19,9802,19,9814],[19,9815,19,9827],[19,9828,19,9840],[19,9841,19,9853],[19,9854,19,9866],[19,9867,19,9879],[19,9880,19,9892],[19,9893,19,9905],[19,9906,19,9918],[19,9919,19,9931],[19,9932,19,9944],[19,9945,19,9957],[19,9958,19,9970],[19,9971,19,9983],[19,9984,19,9996],[19,9997,19,10009],[19,10010,19,10022],[19,10023,19,10035],[19,10036,19,10048],[19,10049,19,10061],[19,10062,19,10074],[19,10075,19,10087],[19,10088,19,10100],[19,10101,19,10113],[19,10114,19,10126],[19,10127,19,10139],[19,10140,19,10152],[19,10153,19,10165],[19,10166,19,10178],[19,10179,19,10191],[19,10192,19,10204],[19,10205,19,10217],[19,10218,19,10230],[19,10231,19,10243],[19,10244,19,10256],[19,10257,19,10269],[19,10270,19,10282],[19,10283,19,10295],[19,10296,19,10308],[19,10309,19,10321],[19,10322,19,10334],[19,10335,19,10347],[19,10348,19,10360],[19,10361,19,10373],[19,10374,19,10386],[19,10387,19,10399],[19,10400,19,10412],[19,10413,19,10425],[19,10426,19,10438],[19,10439,19,10451],[19,10452,19,10464],[19,10465,19,10477],[19,10478,19,10490],[19,10491,19,10503],[19,10504,19,10516],[19,10517,19,10529],[19,10530,19,10542],[19,10543,19,10555],[19,10556,19,10568],[19,10569,19,10581],[19,10582,19,10594],[19,10595,19,10607],[19,10608,19,10620],[19,10621,19,10633],[19,10634,19,10646],[19,10647,19,10659],[19,10660,19,10672],[19,10673,19,10685],[19,10686,19,10698],[19,10699,19,10711],[19,10712,19,10724],[19,10725,19,10737],[19,10738,19,10750],[19,10751,19,10763],[19,10764,19,10776],[19,10777,19,10789],[19,10790,19,10802],[19,10803,19,10815],[19,10816,19,10828],[19,10829,19,10841],[19,10842,19,10854],[19,10855,19,10867],[19,10868,19,10880],[19,10881,19,10893],[19,10894,19,10906],[19,10907,19,10919],[19,10920,19,10932],[19,10933,19,10945],[19,10946,19,10958],[19,10959,19,10971],[19,10972,19,10984],[19,10985,19,10997],[19,10998,19,11010],[19,11011,19,11023],[19,11024,19,11036],[19,11037,19,11049],[19,11050,19,11062],[19,11063,19,11075],[19,11076,19,11088],[19,11089,19,11101],[19,11102,19,11114],[19,11115,19,11127],[19,11128,19,11140],[19,11141,19,11153],[19,11154,19,11166],[19,11167,19,11179],[19,11180,19,11192],[19,11193,19,11205],[19,11206,19,11218],[19,11219,19,11231],[19,11232,19,11244],[19,11245,19,11257],[19,11258,19,11270],[19,11271,19,11283],[19,11284,19,11296],[19,11297,19,11309],[19,11310,19,11322],[19,11323,19,11335],[19,11336,19,11348],[19,11349,19,11361],[19,11362,19,11374],[19,11375,19,11387],[19,11388,19,11400],[19,11401,19,11413],[19,11414,19,11426],[19,11427,19,11439],[19,11440,19,11452],[19,11453,19,11465],[19,11466,19,11478],[19,11479,19,11491],[19,11492,19,11504],[19,11505,19,11517],[19,11518,19,11530],[19,11531,19,11543],[19,11544,19,11556],[19,11557,19,11569],[19,11570,19,11582],[19,11583,19,11595],[19,11596,19,11608],[19,11609,19,11621],[19,11622,19,11634],[19,11635,19,11647],[19,11648,19,11660],[19,11661,19,11673],[19,11674,19,11686],[19,11687,19,11699],[19,11700,19,11712],[19,11713,19,11725],[19,11726,19,11738],[19,11739,19,11751],[19,11752,19,11764],[19,11765,19,11777],[19,11778,19,11790],[19,11791,19,11803],[19,11804,19,11816],[19,11817,19,11829],[19,11830,19,11842],[19,11843,19,11855],[19,11856,19,11868],[19,11869,19,11881],[19,11882,19,11894],[19,11895,19,11907],[19,11908,19,11920],[19,11921,19,11933],[19,11934,19,11946],[19,11947,19,11959],[19,11960,19,11972],[19,11973,19,11985],[19,11986,19,11998],[19,11999,19,12011],[19,12012,19,12024],[19,12025,19,12037],[19,12038,19,12050],[19,12051,19,12063],[19,12064,19,12076],[19,12077,19,12089],[19,12090,19,12102],[19,12103,19,12115],[19,12116,19,12128],[19,12129,19,12141],[19,12142,19,12154],[19,12155,19,12167],[19,12168,19,12180],[19,12181,19,12193],[19,12194,19,12206],[19,12207,19,12219],[19,12220,19,12232],[19,12233,19,12245],[19,12246,19,12258],[19,12259,19,12271],[19,12272,19,12284],[19,12285,19,12297],[19,12298,19,12310],[19,12311,19,12323],[19,12324,19,12336],[19,12337,19,12349],[19,12350,19,12362],[19,12363,19,12375],[19,12376,19,12388],[19,12389,19,12401],[19,12402,19,12414],[19,12415,19,12427],[19,12428,19,12440],[19,12441,19,12453],[19,12454,19,12466],[19,12467,19,12479],[19,12480,19,12492],[19,12493,19,12505],[19,12506,19,12518],[19,12519,19,12531],[19,12532,19,12544],[19,12545,19,12557],[19,12558,19,12570],[19,12571,19,12583],[19,12584,19,12596],[19,12597,19,12609],[19,12610,19,12622],[19,12623,19,12635],[19,12636,19,12648],[19,12649,19,12661],[19,12662,19,12674],[19,12675,19,12687],[19,12688,19,12700],[19,12701,19,12713],[19,12714,19,12726],[19,12727,19,12739],[19,12740,19,12752],[19,12753,19,12765],[19,12766,19,12778],[19,12779,19,12791],[19,12792,19,12804],[19,12805,19,12817],[19,12818,19,12830]],"merged_total":2589,"flags":["merged_cut"]}
["附件2："]
["遂溪县创建“四小园”试点项目入库统计表"]
["填报单位（盖章）：岭北镇人民政府"]
["序号","镇","行政村","自然村","户数","主要建设内容",null,"项目进展情况",null,"总投资（万）",null,null,"备注"]
[{"$nulls":5},"公共区域","群众房前屋后","计划完成\n时间","项目实施情况","财政\n资金","自筹\n资金","合计"]
[]
[1,"岭北","西塘","西塘村",143,"“小公园”项目建设1个，1200平方米，购置桌椅两套“小菜园”“小果园”“小花园”15个，面积约2600平方米","共有45户参与“四小园”建设，面积约2600平方米",2020.12,"规划中",12,0,12,{"$nulls":7},"‘"]
[2,"岭北","西塘","东塘上村",79,"“小公园”项目建设1个，1100平方米，购置桌椅两套“小菜园”“小果园”“小花园”10个，面积约2000平方米","共有32户参与“四小园”建设，面积约2000平方米",2020.12,"规划中",9,0,9]
[3,"岭北","西塘","东塘下村",133,"“小公园”项目建设1个，1000平方米，购置桌椅两套“小菜园”“小果园”“小花园”16个，面积约3000平方米","共有40户参与“四小园”建设，面积约3000平方米",2020.12,"规划中",12,0,12]
[4,"岭北","西塘","下洋村",40,"“小公园”项目建设1个，500平方米，购置桌椅两套“小菜园”“小果园”“小花园”6个，面积约800平方米","共有8户参与“四小园”建设，面积约900平方米",2020.12,"规划中",6,0,6]
[5,"岭北","西塘","肖简村",134,"“小公园”项目建设1个，1200平方米，购置桌椅两套“小菜园”“小果园”“小花园”14个，面积约2600平方米","共有42户参与“四小园”建设，面积约2600平方米",2020.12,"规划中",12,0,12]
[6,"岭北","西塘","边村",79,"“小公园”项目建设1个，600平方米，购置桌椅两套“小菜园”“小果园”“小花园”12个，面积约2000平方米","共有24户参与“四小园”建设，面积约2000平方米",2020.12,"规划中",8,0,8]
[7,"岭北","西塘","罗门塘村",42,"“小果园”“小菜园”6个，面积约2000平方米","共有8户参与“四小园”建设，面积约2000平方米",2020.12,"规划中",1,0,1]
["合计：",{"$nulls":8},60,0,60]
["注：1.“项目实施情况”如规划中、建设中、已完成、管护中等；2.请勿更改表格，并按表中规定的单位填写。"]
["填表人：",{"$nulls":4},"联系电话：","分管领导：",null,"镇主要领导："]
[]
["附件2："]
["遂溪县打造“四小园”试点项目入库统计表"]
["填报单位（盖章）：乌塘镇人民政府"]
["序号","镇","行政村","自然村","户数","主要建设内容",null,"项目进展情况",null,"总投资（万）",null,null,"备注"]
[{"$nulls":5},"公共区域","群众房前屋后","计划完成\n时间","项目实施情况","财政资金","自筹资金","合计"]
[1,"乌塘","边草塘","芳流墩",26,"小公园2个，600平方米；购置文化、娱乐配套设施（如桌椅、健身器材）2套；小花园、小果园、小菜园10个，面积约2000平方米","共有18户参与“四小园”建设，面积约1600平方米",44136,"建设中",20,null,20]
[1,"乌塘","边草塘","芳流墩",26,"小公园2个，600平方米；购置文化、娱乐配套设施（如桌椅、健身器材）2套；小花园、小果园、小菜园10个，面积约2000平方米","共有18户参与“四小园”建设，面积约1600平方米","2020-11-01","建设中",20,null,{"$f":"J24+K24","v":20}]
[2,"乌塘","邦塘","邦塘",100,"小公园1个，200平方米；购置桌椅2套；小花园、小果园、小菜园10个，面积约2000平方米","共有35户参与“四小园”建设，面积约2000平方米","2020-11-01","建设中",10,1,11]
[3,"乌塘","安至塘","安至塘",89,"小公园1个，200平方米；购置桌椅2套；小花园、小果园、小菜园10个，面积约2000平方米","共有20户参与“四小园”建设，面积约2000平方米","2020-11-01","建设中",10,2,12]
[4,"乌塘","陆屋","陆上",77,"小公园1个，200平方米；购置桌椅2套；小花园、小果园、小菜园10个，面积约2000平方米","共有25户参与“四小园”建设，面积约2000平方米","2020-11-01","建设中",10,null,10]
[5,"乌塘","米塘","周屋",43,"小公园1个，200平方米；购置文化、娱乐配套设施（如桌椅、健身器材）1套；小花园、小果园、小菜园10个，面积约1500平方米","共有25户参与“四小园”建设，面积约1200平方米","2020-11-01","建设中",20,2,22]
[6,"乌塘","米塘","米塘",61,"购置文化、娱乐配套设施（如桌椅、健身器材）2套；小花园、小果园、小菜园10个，面积约2001平方米","共有30户参与“四小园”建设，面积约1200平方米","2020-12-01","建设中",15,null,15]
[7,"乌塘","庞村","庞村",93,"购置文化、娱乐配套设施（如桌椅、健身器材）2套；小花园、小果园、小菜园10个，面积约2000平方米","共有30户参与“四小园”建设，面积约1800平方米","2020-12-01","建设中",10,1,11]
[8,"乌塘","白水塘","白水塘",92,"购置文化、娱乐配套设施（如桌椅、健身器材）2套；小花园、小果园、小菜园10个，面积约2001平方米","共有30户参与“四小园”建设，面积约1500平方米","2020-12-01","建设中",10,null,10]
[9,"乌塘","梁村","梁村",54,"小公园1个，200平方米；购置文化、娱乐配套设施（如桌椅、健身器材）2套；小花园、小果园、小菜园10个，面积约2002平方米","共有18户参与“四小园”建设，面积约1300平方米","2020-12-01","建设中",10,2,12]
[10,"乌塘","安贡","安贡",151,"购置文化、娱乐配套设施（如桌椅、健身器材）2套；小花园、小果园、小菜园10个，面积约2500平方米","共有45户参与“四小园”建设，面积约2300平方米","2020-12-01","建设中",10,null,10]
[11,"乌塘","安贡","曲枙",47,"小公园1个，200平方米；购置文化、娱乐配套设施（如桌椅、健身器材）2套；小花园、小果园、小菜园10个，面积约2000平方米","共有15户参与“四小园”建设，面积约1800平方米","2020-12-01","建设中",10,null,10]
[12,"乌塘","湛川","湛川",347,"小公园1个，400平方米；购置文化、娱乐配套设施（如桌椅、健身器材）3套；小花园、小果园、小菜园10个，面积约2500平方米","共有55户参与“四小园”建设，面积约2000平方米","2020-12-01","建设中",20,3,23]
[13,"乌塘","新屋","新屋",106,"购置文化、娱乐配套设施（如桌椅、健身器材）3套；小花园、小果园、小菜园10个，面积约2500平方米","共有30户参与“四小园”建设，面积约2000平方米","2020-12-01","建设中",10,3,13]
[14,"乌塘","安铺仔","安铺仔",108,"购置文化、娱乐配套设施（如桌椅、健身器材）3套；小花园、小果园、小菜园10个，面积约2500平方米","共有30户参与“四小园”建设，面积约2000平方米","2020-12-01","建设中",10,2,12]
[15,"乌塘","迈机西","迈机西",111,"小公园1个，200平方米；购置桌椅2套；小花园、小果园、小菜园10个，面积约2000平方米","共有25户参与“四小园”建设，面积约2000平方米","2020-12-01","建设中",20,2,22]
[16,"乌塘","外坡","外坡",84,"小公园1个，200平方米；购置桌椅2套；小花园、小果园、小菜园10个，面积约2000平方米","共有25户参与“四小园”建设，面积约2000平方米","2020-12-01","建设中",20,1,21]
[17,"乌塘","北安","北安",175,"小公园1个，200平方米；购置桌椅2套；小花园、小果园、小菜园12个，面积约2000平方米","共有28户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",15,null,15]
[18,"乌塘","周龙","周龙",138,"小公园1个，100平方米；购置桌椅3套；小花园、小果园、小菜园15个，面积约2000平方米","共有25户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",15,null,15]
[19,"乌塘","乌塘圩","乌塘圩",220,"购置桌椅2套；小花园、小果园、小菜园15个，面积约2000平方米","共有25户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",10,null,10]
[20,"乌塘","边草塘","边草塘",182,"购置桌椅3套；小花园、小果园、小菜园12个，面积约2100平方米","共有22户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",20,null,20]
[21,"乌塘","乌塘岭","乌塘岭",171,"小公园1个，100平方米；购置桌椅2套；小花园、小果园、小菜园12个，面积约2000平方米","共有29户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",10,null,10]
[22,"乌塘","安至塘","迈机东",25,"购置桌椅3套；小花园、小果园、小菜园16个，面积约2000平方米","共有18户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",5,null,5]
[23,"乌塘","山口陈","山口陈",189,"小公园1个，200平方米；购置桌椅3套；小花园、小果园、小菜园10个，面积约2000平方米","共有25户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",10,null,10]
[24,"乌塘","山口王","山口王",147,"小公园1个，200平方米；购置桌椅2套；小花园、小果园、小菜园10个，面积约2000平方米","共有22户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",10,null,10]
[25,"乌塘","边板","边板",118,"购置桌椅2套；小花园、小果园、小菜园12个，面积约2000平方米","共有22户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",10,null,10]
[26,"乌塘","油河","油河",44,"购置桌椅2套；小花园、小果园、小菜园12个，面积约2000平方米","共有25户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",10,null,10]
[27,"乌塘","陆屋","陆下",81,"小公园1个，200平方米；购置桌椅2套；小花园、小果园、小菜园10个，面积约2000平方米","共有30户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",10,null,10]
[28,"乌塘","金屋","金屋",71,"购置桌椅3套；小花园、小果园、小菜园13个，面积约2200平方米","共有18户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",15,null,15]
[29,"乌塘","罗屋","罗屋",297,"小公园1个，200平方米；购置桌椅2套；小花园、小果园、小菜园15个，面积约2300平方米","共有35户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",15,1,16]
[30,"乌塘","扫手塘","扫手塘",79,"小公园1个，200平方米；购置桌椅2套；小花园、小果园、小菜园10个，面积约2000平方米","共有25户参与“四小园”建设，面积约2000平方米","2020-12-01","规划中",10,null,10]
["合计",{"$nulls":8},380,20,400]
["注：1.“项目实施情况”如规划中、建设中、已完成、管护中等；2.请勿更改表格，并按表中规定的单位填写。"]
["填表人",{"$nulls":3},"联系电话：18718181618                        分管领导：",null," 分管领导：",null,"镇主要领导："]
[]
["附件2："]
["遂溪县创建“四小园”试点项目入库统计表"]
["填报单位（盖章）：遂溪县遂城镇人民政府"]
["序号","镇","行政村","自然村","户数","主要建设内容",null,"项目进展情况",null,"总投资（万）",null,null,"备注"]
[{"$nulls":5},"公共区域","群众房前屋后","计划完成\n时间","项目实施情况","财政\n资金","自筹\n资金","合计"]
[]
[1,"遂城","礼村","礼下村",144,"小公园700平方,铺彩砖200m2，桌椅2套",null,"2020.12.30","规划中",8,3,11]
[2,"遂城","礼村","礼上村",101,"小公园600平方，铺彩砖100m2，桌椅3套",null,"2020.12.30","规划中",8,1,9]
[3,"遂城","礼村","礼一村",63,"小公园700平方，铺彩砖200m2，桌椅2套",null,"2020.12.30","规划中",8,4,12]
[4,"遂城","礼村","白石头村",70,"小公园680平方，铺彩砖100m2，桌椅2套",null,"2020.12.30","规划中",8,2,10]
[5,"遂城","礼村","瓦屋岭村",73,"小公园700平方，铺彩砖100m2，桌椅2套",null,"2020.12.30","规划中",8,3,11]
[6,"遂城","礼村","荔枝山村",42,"小公园700平方，铺彩砖100m2，桌椅3套",null,"2020.12.30","规划中",8,1,9]
[7,"遂城","礼村","昌考村",56,"小公园700平方，铺彩砖150m2，桌椅2套",null,"2020.12.30","规划中",8,4,12]
["合计：",{"$nulls":3},549,"4800平方",{"$nulls":3},56,18,74]
["注：1.“项目实施情况”如规划中、建设中、已完成、管护中等；2.请勿更改表格，并按表中规定的单位填写。"]
["填表人：蔡裕平                \n\n  \n",{"$nulls":4},"联系电话：7768711                                ","分管领导：        ",null,"镇主要领导："]