{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["草潭镇 (2)","888","0000"],"not_rendered":{"external_links":1,"defined_names":9},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"草潭镇 (2)","index":0,"n_rows":8,"n_cols":17,"rows_kept":8,"merged":[[0,0,0,14],[1,0,1,4],[1,9,1,10],[1,13,1,14],[2,0,4,0],[2,1,4,1],[2,2,4,2],[2,3,4,3],[2,4,4,4],[2,5,4,5],[2,6,4,6],[2,7,3,8],[2,9,2,13],[2,14,4,14],[3,9,4,9],[3,10,3,12],[3,13,4,13],[7,0,7,14]],"flags":["formulas_cached_only"]}
["遂溪县草潭镇2020年省级涉农资金(农村人居环境整治类）建设项目调整公示"]
["填报单位（盖章）：草潭镇人民政府",{"$nulls":8},"日期：",null,"2020.10.28"]
["序号","镇","行政村","自然村","项目类别","项目名称","主要建设内容","项目进展情况",null,"总投资（万元）",{"$nulls":4},"备注"]
[{"$nulls":9},"总计","财政资金",null,null,"自筹资金"]
[{"$nulls":7},"计划时间","项目实施情况",null,"合计","中央财政","涉农资金",null,null,"施工方","已签付（万元）"]
[1,"草潭镇","石杨村委","塘南村","人畜分离","草潭镇塘南村鸡舍建设项目","建设鸡舍",null,null,3,null,null,{"v":2,"d":"2.00"},1,"调整前取消"]
[1,"草潭镇","石杨村委","姓张村","路灯建设","草潭镇姓张村路灯建设项目","路灯10盏",null,null,3,null,null,2,1,"调整后","张武"]
["注：1.“项目类别”填写村道建设、垃圾处理设施建设、村容村貌提升、人畜分离、路灯建设等。\n    2.“项目名称”要求精确填写，如XX镇XX村乡村道路建设项目。\n    3.请勿更改表格，并按表中规定的单位填写。\n    "]

{"sheet":"888","index":1,"n_rows":43,"n_cols":16,"rows_kept":43,"merged":[[1,0,1,14],[2,0,2,4],[2,9,2,10],[2,13,2,14],[3,0,5,0],[3,1,5,1],[3,2,5,2],[3,3,5,3],[3,4,5,4],[3,5,5,5],[3,6,5,6],[3,7,4,8],[3,9,3,13],[3,14,5,14],[4,9,5,9],[4,10,4,12],[4,13,5,13],[41,0,41,4],[41,6,41,8],[41,9,41,13],[42,0,42,14]],"flags":["formulas_cached_only"]}
["附件2"]
["遂溪县2020年省级涉农资金(农村人居环境整治类）项目入库统计表"]
["填报单位（盖章）：草潭镇人民政府",{"$nulls":8},"日期："]
["序号","镇","行政村","自然村","项目类别","项目名称","主要建设内容","项目进展情况",null,"总投资（万元）",{"$nulls":4},"备注"]
[{"$nulls":9},"总计","财政资金",null,null,"自筹资金"]
[{"$nulls":7},"计划时间","项目实施情况",null,"合计","中央财政","涉农资金"]
[1,"草潭镇","新建村委会","克村","村容村貌提升","草潭镇新建村委会克村村容村貌提升建设项目","小公园1000平方","2020-09-01",null,22.5,{"$nulls":3},7.5]
[2,"草潭镇","新建村委会","埠头仔村","村容村貌提升","草潭镇新建村委会埠头仔村容村貌提升建设项目","小公园800平方","2020-09-01",null,22.5,null,null,{"v":10,"d":"10.00"},7.5]
[3,"草潭镇","坎尾村","坎尾村","路灯建设","草潭镇坎尾村环村路灯建设","太阳能路灯35盏",2020.8,null,15,null,null,{"v":10,"d":"10.00"},5]
[4,"草潭镇","坎尾村","坎尾村","村容村貌提升","草潭镇坎尾村村委办公楼前健身休闲公园","建设2000平方米小公园",2020.8,null,25,null,null,{"v":15,"d":"15.00"},10]
[null,"草潭镇","坎尾村","坎尾村","村容村貌提升",null,"四小园建设",null,null,7.5,null,null,{"v":5,"d":"5.00"},2.5]
[5,"草潭","姓蔡村","姓蔡村","村道建设","村道建设","村道硬底化4米*500米*18厘米","2020.10.",null,25,null,null,{"v":11.5,"d":"11.50"},8.5]
[6,"草潭","姓蔡村","姓蔡村","巷道建设","巷道建设","巷道硬底化2.5米*600米*15厘米","2020.10.",null,20,null,null,{"v":12,"d":"12.00"},8]
[null,"草潭","姓蔡村","姓蔡村","村容村貌提升",null,"四小园建设",null,null,7.5,null,null,{"v":5,"d":"5.00"},2.5]
[7,"草潭","姓庞村","姓庞村","村容村貌提升",null,"四小园建设","2020-10-01T02:24:00",null,5,null,null,{"v":3,"d":"3.00"},2]
[8,"草潭","姓庞村","姓庞村","公共文化设施建设","草潭镇姓庞村公共文化设施建设","文休广场","2020-10-01",null,10,null,null,{"v":6.5,"d":"6.50"},3.5]
[9,"草潭镇","布屋","布屋村","村道建设","草潭镇布屋村村道硬底化","村道硬底化：长180米×宽4米×厚18厘米","2020.10.",null,9,null,null,{"v":6,"d":"6.00"},3]
[10,"草潭镇","东港村委","东港仔村","村容村貌提升","草潭镇东港仔村村庄围栏美化绿化","建设小公园1200㎡","2020.10.",null,23,null,null,{"v":13,"d":"13.00"},10,null,13]
[11,"草潭镇","东港村委","北二村","公共文化设施建设","草潭镇北二村公共文化设施建设","建设休闲公园4000㎡","2020.10.",null,35,null,null,{"v":12,"d":"12.00"},12,null,12]
[null,"草潭镇","东港村委","北一村","村道建设",{"$nulls":4},22.5,null,null,{"v":20,"d":"20.00"},7.5,null,20]
[12,"草潭镇","罗屋村委","长洪村","亮化建设","长洪村亮化路灯建设","50盏太阳能路灯","2020.10.",null,15,null,null,{"v":8,"d":"8.00"},5]
[13,"草潭","姓毛村","姓毛村","公共文化设施建设","草潭镇姓毛村公共文化设施建设","建设小公园800㎡","2020-11-01",null,30,null,null,{"v":15,"d":"15.00"},10]
[14,"草潭镇","姓马村委","姓马村","村容村貌提升","草潭镇姓马村公共文化设施建设","小公园500平方米",2020.9,null,21,null,null,{"v":14,"d":"14.00"},7]
[15,"草潭镇","北拉村委会","北拉村","路灯建设","草潭镇北拉村委会北拉村路灯建设","太阳能路灯15盏","2020-09-01",null,5.1,null,null,{"v":3.4,"d":"3.40"},1.7]
[16,"草潭镇","北拉村委会","东村","路灯建设","草潭镇北拉村委会东村路灯建设","太阳能路灯15盏","2020-09-01",null,5.1,null,null,{"v":3.4,"d":"3.40"},1.7]
[17,"草潭镇","北拉村委会","港尾新村","路灯建设","草潭镇北拉村委会港尾新村路灯建设","太阳能路灯20盏","2020-09-01",null,6.8,null,null,{"v":4.5,"d":"4.50"},2.3]
[18,"草潭潭","荔枝","荔枝山","路灯建设","草潭镇荔枝山村路灯建设","50盏太阳能路灯","2020-09-01",null,16,{"$nulls":3},6]
[19,"草潭潭","田头壳","田头壳","路灯建设","草潭镇田头壳村路灯建设","50盏太阳能路灯","2020-09-01",null,18,null,null,{"v":12,"d":"12.00"},6]
[20,"草潭镇","石杨村委","姓蔡村","道路硬底化建设","草潭镇姓蔡道路硬底化建设","道路硬底化建设180ｍ×4×18","2020.11.",null,14.3,null,null,{"v":9.5,"d":"9.50"},4.8]
[21,"草潭镇","石杨村委","姓张村","亮化工程","草潭镇姓张村路灯建设","路灯12盏","2020.11.",null,3.6,{"$nulls":3},1.2]
[null,"草潭镇","石杨村委","塘南村","人畜分离",null,"建设鸡舍",null,null,3,null,null,{"v":2,"d":"2.00"},1]
[22,"草潭镇","草潭社区","草潭圩","道路硬底化建设","道路硬底化建设","道路硬底化建设327ｍ×6M×20CM","2020.11.",null,40,null,null,{"v":26,"d":"26.00"},14]
[23,"草潭镇","钗仔村委","河仔边村","路灯建设","草潭镇钗仔村委河仔边路灯建设","路灯建设40盏","2020-09-01",null,13.6,null,null,{"v":9,"d":"9.00"},4.6]
[24,"草潭镇","钗仔村委","茅山村","小公园","草潭镇钗仔村委茅山村小公园建设","建设2000平方米小公园","2020-09-01",null,40,null,null,{"v":26.5,"d":"26.50"},13.5]
[25,"草潭镇","钗仔村委","茅山村","人畜分离","草潭镇钗仔村委茅山村牛栏建设","牛栏9间","在建",null,2.7,{"$nulls":3},0.9]
[26,"草潭镇","钗仔村委","草潭大村","路灯建设","草潭大村路灯建设","路灯建设70盏","2020-09-01",null,22.4,null,null,{"v":12.9,"d":"12.90"},7.5]
[27,"草潭镇","旧庙村委会","基头村","亮化工程","草潭镇基头村路灯建设","路灯32盏","2020.11.",null,11.52,null,null,{"v":7.6,"d":"7.60"},3.84,null,3.8]
[28,"草潭镇","旧庙村委会","南塘村","亮化工程","草潭镇南塘村路灯建设","路灯30盏","2020.11.",null,10.799999999999999,null,null,{"v":7.199999999999999,"d":"7.20"},3.6]
[29,"草潭镇","麻公村委会","塘仔笃村","村道建设","草潭镇麻公村委会塘仔笃村道路硬底化建设项目","村道硬底化：长1000米×宽4米×厚15厘米","2020-09-01",null,45,null,null,{"v":30,"d":"30.00"},15]
[34,"草潭镇","天德村委会","岸基村","巷道建设","巷道建设","1000m×4m×12cm",2020.9,null,45,null,null,{"v":30,"d":"30.00"},15]
["合计",{"$nulls":8},618.4200000000001,0,0,350,214.14]
["填表人：",{"$nulls":5},"联系电话：",null,null,"镇主要领导："]
["注：1.“项目类别”填写村道建设、垃圾处理设施建设、村容村貌提升、人畜分离、路灯建设等。\n    2.“项目名称”要求精确填写，如XX镇XX村乡村道路建设项目。\n    3.请勿更改表格，并按表中规定的单位填写。\n    "]

{"sheet":"0000","index":2,"n_rows":90,"n_cols":15,"rows_kept":90,"merged":[[1,0,1,14],[2,0,2,4],[2,9,2,10],[2,13,2,14],[3,0,5,0],[3,1,5,1],[3,2,5,2],[3,3,5,3],[3,4,5,4],[3,5,5,5],[3,6,5,6],[3,7,4,8],[3,9,3,13],[3,14,5,14],[4,9,5,9],[4,10,4,12],[4,13,5,13],[88,0,88,4],[88,6,88,8],[88,9,88,13],[89,0,89,14]],"flags":["formulas_cached_only"]}
["附件2"]
["遂溪县2020年省级涉农资金(农村人居环境整治类）项目入库统计表"]
["填报单位（盖章）：草潭镇人民政府",{"$nulls":8},"日期："]
["序号","镇","行政村","自然村","项目类别","项目名称","主要建设内容","项目进展情况",null,"总投资（万元）",{"$nulls":4},"备注"]
[{"$nulls":9},"总计","财政资金",null,null,"自筹资金"]
[{"$nulls":7},"计划时间","项目实施情况",null,"合计","中央财政","涉农资金"]
[1,"草潭镇","红莳地","红莳地小村","公共文化设施建设","草潭镇红莳地小村公共文化设施建设","建设篮球场640㎡     (水磨石)","2020.10.",null,17,null,null,11,6]
[2,"草潭镇","红莳地","红莳地小村","公共文化设施建设","草潭镇红莳地小村公共文化设施建设","建设休闲场所400㎡","2020.10.",null,3,null,null,2,1]
[3,"草潭镇","红莳地","红莳地小村","村道建设","草潭镇红莳地小村巷道建设","巷道硬底化250×2米",2020.11,null,10,null,null,6,4]
[4,"草潭镇","红莳棚","红莳棚村","道路硬底化建设","草潭镇红莳棚村村道巷道硬底化","村道巷道硬底化：宽3米，长1000米",2020.9,null,45,null,null,30,15]
[5,"草潭镇","红莳地村","红莳地大村","村道巷道建设","草潭镇红莳地大村巷道建设","巷道硬底化1800m长×2m宽×12㎝厚","2020.10.",null,38,null,null,25.4,12.6]
[6,"草潭镇","红莳地村","红莳地大村","公共文化设施建设","草潭镇红莳地大村公共文化设施建设","建设器材10套",2020.11,null,1.5,null,null,1,0.5]
[7,"草潭镇","红莳地","红莳地小村","公共文化设施建设","草潭镇红莳地小村公共文化设施建设","建设篮球场640㎡ ","2020.10.",null,17,null,null,11.3,5.7]
[8,"草潭镇","红莳地","红莳地小村","公共文化设施建设","草潭镇红莳地小村公共文化设施建设","建设休闲场所400㎡","2020.10.",null,3.2,null,null,2.1,1.1]
[9,"草潭镇","红莳地","红莳地小村","村道建设","草潭镇红莳地小村巷道建设","巷道硬底化250m长×2m宽×12㎝厚",2020.11,null,10,null,null,6.7,3.3]
[10,"草潭镇","艾仔寮","艾仔寮村","巷道建设","草潭镇艾仔寮村巷道硬底化建设","巷道硬底化200m长×4ｍ宽×0.18m厚","2020.10.",null,10,null,null,7,3]
[11,"草潭镇","艾仔寮","艾仔寮村","路灯建设","草潭镇艾仔寮村路灯建设","路灯建设76盏","2020.9.",null,30,null,null,20,10]
[12,"草潭镇","新建村委会","响地村","道路硬底化建设","草潭镇新建村委会响地村道路硬底化建设项目","宽4米，厚18公分，长150米","2020-09-01",null,12,null,null,8,4]
[13,"草潭镇","新建村委会","响地村","村容村貌提升","草潭镇新建村委会响地村村容村貌提升建设项目","小公园1000平方","2020-09-01",null,30,null,null,20,10]
[14,"草潭镇","新建村委会","埠头仔村","村容村貌提升","草潭镇新建村委会埠头仔村容村貌提升建设项目","小公园700平方","2020-09-01",null,15,null,null,10,5]
[15,"草潭镇","新建村委会","克村","道路硬底化建设","草潭镇新建村委会克村道路硬底化建设项目","宽4米，厚18公分，长200米","2020-09-01",null,15,null,null,10,5]
[16,"草潭镇","新建村委会","活港村","道路硬底化建设","草潭镇新建村委会活港村道路硬底化建设项目","宽4米，厚18公分，长200米","2020-09-01",null,15,null,null,10,5]
[17,"草潭镇","坎尾村","坎尾村","路灯建设","草潭镇坎尾村环村路灯建设","太阳能路灯35盏",2020.8,null,15,null,null,10,5]
[18,"草潭镇","坎尾村","坎尾村","村容村貌提升","草潭镇坎尾村村委办公楼前健身休闲公园","建设2000平方米小公园",2020.8,null,30,null,null,20,10]
[19,"草潭镇","珍珠湾","珍珠湾","村道建设","草潭镇珍珠湾村村道硬底化","村道硬底化：长400米×宽4米×厚18厘米","2020.11.",null,20,null,null,13.5,6.5]
[20,"草潭镇","布屋","布屋村","村道建设","草潭镇布屋村村道硬底化","村道硬底化：长180米×宽4米×厚18厘米","2020.10.",null,9,null,null,6,3]
[21,"草潭镇","瓦窑墩","瓦窑墩村","村道建设","草潭镇瓦窑墩村村道硬底化","村道硬底化：长180米×宽4米×厚18厘米","2020.10.",null,9,null,null,6,3]
[22,"草潭","姓蔡村","姓蔡村","村道建设","村道建设","村道硬底化4米*500米*18厘米","2020.10.",null,25,null,null,18,7]
[23,"草潭","姓蔡村","姓蔡村","巷道建设","巷道建设","巷道硬底化2.5米*600米*15厘米","2020.10.",null,20,null,null,12,8]
[24,"草潭镇","东港村委","东港仔村","村容村貌提升","草潭镇东港仔村村庄围栏美化绿化","建设休闲场所1200㎡","2020.10.",null,30,null,null,20,10]
[25,"草潭镇","东港村委","罗湾村","公共文化设施建设","草潭镇罗湾村公共文化设施建设","建设小公园400㎡",20209.9,null,15,null,null,10,5]
[26,"草潭镇","东港村委","罗湾村","公共文化设施建设","草潭镇罗湾村公共文化设施建设","建设篮球场550㎡",2020.9,null,15,null,null,10,5]
[27,"草潭镇","东港村委","北二村","公共文化设施建设","草潭镇北二村公共文化设施建设","建设休闲公园4000㎡","2020.10.",null,35,null,null,25,10]
[28,"草潭镇","罗屋村委","长洪村","亮化建设","长洪村亮化路灯建设","50盏太阳能路灯","2020.10.",null,15,null,null,10,5]
[29,"草潭镇","罗屋村委","大墩村","亮化建设","大墩村亮化路灯建设","60盏太阳能路灯","2020.10.",null,18,null,null,12,6]
[30,"草潭镇","下六圩社区","坎头村","村容村貌提升","围栏保绿","建设围栏1500平方",2020.9,null,3.05,null,null,2.25,0.8]
[31,"草潭镇","下六圩社区","坎头村","村容村貌提升","排雨水沟","建设水沟3.7公里",2020.9,null,14.8,null,null,11.1,3.7]
[32,"草潭镇","下六圩社区","新村仔村","村容村貌提升","围栏保绿","建设围栏1050平方",2020.9,null,2.175,null,null,1.575,0.6]
[33,"草潭镇","下六圩社区","新村仔村","村容村貌提升","排雨水沟","建设水沟3.7公里",2020.9,null,14.8,null,null,11.1,3.7]
[34,"草潭镇","下六圩社区","下六圩村","村容村貌提升","围栏保绿","建设围栏3700平方",2020.9,null,2.525,null,null,0.525,2]
[35,"草潭镇","下六圩社区","柴埠村","村容村貌提升","围栏保绿","建设围栏350平方",2020.9,null,0.705,null,null,0.525,0.18]
[36,"草潭","姓毛村","姓毛村","公共文化设施建设","草潭镇姓毛村公共文化设施建设","建设小公园800㎡","2020-11-01",null,24,null,null,16,8]
[37,"草潭","姓毛村","姓毛村","公共文化设施建设","草潭镇姓毛村公共文化设施建设","建设篮球场600㎡","2020-11-01",null,12,null,null,8,4]
[38,"草潭","姓欧村","姓欧村","公共文化设施建设","草潭镇姓欧村公共文化设施建设","建设小公园1500㎡","2020-11-01",null,30,null,null,20,10]
[39,"草潭","铺仔村","铺仔村","公共文化设施建设","草潭镇铺仔村公共文化设施建设","建设休闲场所150㎡","2020-11-01",null,6,null,null,4,2]
[40,"草潭","铺仔村","铺仔村","公共文化设施建设","草潭镇铺仔村公共文化设施建设","建设篮球场600㎡","2020-11-01",null,12,null,null,8,4]
[41,"草潭","北灶尾村","北灶尾村","公共文化设施建设","草潭镇北灶尾村公共文化设施建设","建设小公园400㎡","2020-11-01",null,21,null,null,14,7]
[42,"草潭","北灶尾村","北灶尾村","公共文化设施建设","草潭镇北灶尾村公共文化设施建设","建设篮球场600㎡","2020-11-01",null,12,null,null,8,4]
[43,"草潭镇","姓马村委","姓马村","村容村貌提升","草潭镇姓马村村庄美化、绿化建设","美化、绿化700米",2020.9,null,9,null,null,6,3]
[44,"草潭镇","姓马村委","姓马村","村容村貌提升","草潭镇姓马村公共文化设施建设","小公园500平方米",2020.9,null,21,null,null,14,7]
[45,"草潭镇","下六村委","下六村","村容村貌提升","草潭镇下六村道路美化、绿化建设","绿化200米、种风景树50棵","2020.10",null,9,null,null,6,3]
[46,"草潭镇","北拉村委会","港头村","路灯建设","草潭镇北拉村委会港头村路灯建设","路灯建设12盏","2020-09-01",null,3,null,null,2,1]
[47,"草潭镇","北拉村委会","港头村","村容村貌提升","草潭镇北拉村委会港头村村容村貌提升建设项目","村庄绿化美化","2020-09-01",null,39,null,null,26,13]
[48,"草潭镇","北拉村委会","老村","路灯建设","草潭镇北拉村委会老村路灯建设","路灯建设40盏","2020-09-01",null,15,null,null,10,5]
[49,"草潭","姓庞村","姓庞村","公共文化设施建设","草潭镇姓庞村公共文化设施建设","石登、石台、健身器材一套","2020-10-01T02:24:00",null,5,null,null,3,2]
[50,"草潭","姓庞村","姓庞村","公共文化设施建设","草潭镇姓庞村公共文化设施建设","文休广场","2020-10-01",null,10,null,null,6.5,3.5]
[51,"草潭潭","荔枝","荔枝山","路灯建设","草潭镇荔枝山村路灯建设","50盏太阳能路灯","2020-09-01",null,15,null,null,10,5]
[52,"草潭潭","荔枝","荔枝山","村容村貌提升","草潭镇荔枝山村公共文化设施建设","小公园2000平方","2020-09-01",null,30,null,null,20,10]
[53,"草潭潭","田头壳","田头壳","路灯建设","草潭镇田头壳村路灯建设","50盏太阳能路灯","2020-09-01",null,15,null,null,10,5]
[54,"草潭潭","田头壳","田头壳","村容村貌提升","草潭镇田头壳村公共文化设施建设","小公园800平方","2020-09-01",null,30,null,null,20,10]
[55,"草潭镇","石杨村委","姓蔡村","道路硬底化建设","草潭镇姓蔡道路硬底化建设","道路硬底化建设180ｍ×4×18","2020.11.",null,14.3,null,null,10.8,3.5]
[56,"草潭镇","石杨村委","甜娘村","亮化工程","草潭镇甜娘村路灯建设","路灯30盏","2020.11.",null,13.600000000000001,null,null,10.3,3.3]
[57,"草潭镇","石杨村委","姓张村","亮化工程","草潭镇姓张村路灯建设","路灯30盏","2020.11.",null,13.5,null,null,10.2,3.3]
[58,"草潭镇","草潭社区","草潭圩","道路硬底化建设","道硬底化建设","圩道硬底化建设80ｍ×10ｍ×20","2020.10.",null,12,null,null,8,4]
[59,"草潭镇","草潭社区","草潭圩","文化设施建设","村容村貌提升","建设小公园160㎡","2020.11.",null,2.8,null,null,2.1,0.7]
[60,"草潭镇","草潭社区","草潭圩","道路硬底化建设","道硬底化建设","圩道硬底化建设208ｍ×2ｍ×10","2020.11.",null,4.5,null,null,3,1.5]
[61,"草潭镇","草潭社区","槟榔园","道路硬底化建设","道路硬底化建设","道路硬底化建设735ｍ×4×18","2020.11.",null,45,null,null,30,15]
[62,"草潭镇","钗仔村委","河仔边村","路灯建设","草潭镇钗仔村委河仔边路灯建设","路灯建设40盏","2020-09-01",null,3,null,null,2,1]
[63,"草潭镇","旧庙村委会","基头村","亮化工程","草潭镇基头村路灯建设","路灯32盏","2020.11.",null,14.4,null,null,10.9,3.5]
[64,"草潭镇","旧庙村委会","南塘村","亮化工程","草潭镇南塘村路灯建设","路灯30盏","2020.11.",null,13.5,null,null,10.2,3.3]
[65,"草潭镇","泉水","美翁上村","道路硬底化建设","道硬底化建设","道路硬底化建设800ｍ长×4米宽×12cm","2020.10.",null,41.6,null,null,27.6,14]
[66,"草潭镇","泉水","外坡仔","道路硬底化建设","道路硬底化建设","道路硬底化建设400ｍ×3×12","2020.10.",null,13.2,null,null,8.8,4.4]
[67,"草潭镇","泉水","外坡仔"," 村容村貌提升","外坡仔村村容村貌提升","小公园3000平方","2020.10.",null,60,null,null,16,44]
[68,"草潭镇","泉水","外坡仔","人畜分离"," 牛栏建设"," 牛栏建设18平方x17","2020.10.",null,9,null,null,6,3]
[69,"草潭镇","泉水","黄湖塘村","　路灯建设","草潭镇黄湖塘村路灯建设","　路灯建设34盏","2020.10.",null,10.2,null,null,6.8,3.4]
[70,"草潭镇","泉水","松柏村　","路灯建设","草潭镇松柏村路灯建设","　路灯建设104盏","2020.10.",null,31.2,null,null,20.8,10.4]
[71,"草潭镇","泉水","训基塘村","公共文化设施建设","草潭镇训基塘村公共文化设施建设","建设篮球场640㎡ ",2020.9,null,17,null,null,11.3,5.7]
[72,"草潭镇","泉水","曲塘村","公共文化设施建设","草潭镇曲塘村公共文化设施建设","建设篮球场640㎡ ","2020.10.",null,17,null,null,11.3,5.7]
[73,"草潭镇","泉水","外坡村","　路灯建设","草潭镇外坡村路灯建设","　路灯建设13盏",2020.11,null,3.9,null,null,2.6,1.3]
[74,"草潭镇","泉水","外坡村","村容村貌提升","草潭镇外坡村村容村貌提升建设项目","小公园700平方","2020.10.",null,21,null,null,14,7]
[75,"草潭镇","泉水","北头村","路灯建设","草潭镇北头村路灯建设","路灯建设100盏","2020.10.",null,30,null,null,20,10]
[76,"草潭镇","泉水","北头村","村容村貌提升","草潭镇北头村村容村貌提升建设项目","　绿化2000平方",2020.11,null,40,null,null,10,30]
[77,"草潭镇","泉水","陈家山村","巷道建设","草潭镇陈家山村巷道硬底化建设","巷道硬底化1200m长×3ｍ宽×12m厚","2020.10.",null,39.6,null,null,26.4,13.2]
[78,"草潭镇","泉水","温北","路灯建设","草潭镇温北村路灯建设","路灯建设80盏","2020.9.",null,24,null,null,16,8]
[79,"草潭镇","泉水","中间村","路灯建设","草潭镇中间村路灯建设","路灯建设160盏","2020-09-01",null,48,null,null,30,18]
[80,"草潭镇","泉水","淡塘仔村","道路硬底化建设","草潭镇淡塘仔村道路硬底化建设项目","巷道硬底化1000m长×3ｍ宽×12m厚","2020-10-01",null,33,null,null,22,11]
[81,"草潭镇","麻公村委会","塘仔笃村","村道建设","草潭镇麻公村委会塘仔笃村道路硬底化建设项目","村道硬底化：长1000米×宽4米×厚15厘米","2020-09-01",null,45,null,null,30,15]
["合计",{"$nulls":8},1504.0549999999998,0,0,968.6749999999998,535.3799999999999]
["填表人：罗伯良",{"$nulls":5},"联系电话：13702699285",null,null,"镇主要领导："]
["注：1.“项目类别”填写村道建设、垃圾处理设施建设、村容村貌提升、人畜分离、路灯建设等。\n    2.“项目名称”要求精确填写，如XX镇XX村乡村道路建设项目。\n    3.请勿更改表格，并按表中规定的单位填写。\n    "]